ACME CO. · ENGAGEMENT PROPOSAL

# A quieter system for how Acme ships.

A proposal to design and build a unified content system across Acme's docs, decks, and dashboards.

Prepared by  Dan Sozanski

Design & Build   ·   June 2026

TL;DR  Acme produces a high volume of client-facing collateral with no shared system, so quality drifts and every piece starts from zero. This proposal delivers one design system, a component library, and templates, in three phases over eight weeks.

## Overview

Acme's teams produce proposals, decks, and reporting dashboards independently. Without shared foundations, each piece is rebuilt by hand, brand consistency erodes, and turnaround stays slow.

This engagement establishes a single design system, applies it across every surface, and hands over templates and documentation so the team can produce on-brand work without a designer in the loop.

## Scope of work

### Foundations

- Color, type, spacing, and motion tokens, documented in one source of truth.

- A token playground for live tuning and sign-off.

### Component library

- A catalog of production components across actions, forms, data, and feedback.

- Chart and dashboard widgets for interactive reporting.

### Templates and handover

- Proposal, deck, dashboard, and one-sheet templates.

- Documentation and a working session to hand the system to the team.

## Timeline

Phase 1  Foundations and audit   Weeks 1-2

Phase 2  Component library   Weeks 3-6

Phase 3  Templates and handover   Weeks 7-8

## Investment

| ITEM | DETAIL | AMOUNT |
| --- | --- | --- |
| Foundations | Tokens, audit, playground | $6,000 |
| Component library | Catalog + chart widgets | $14,000 |
| Templates & handover | Templates, docs, session | $8,000 |
| Total | Fixed fee, 50% to start | $28,000 |

Fixed fee. The amount above is the whole engagement, not an estimate.

## Terms

Fixed fee, billed 50% on signature and 50% on delivery. Timeline assumes one round of consolidated feedback per phase. Either party may pause with two weeks' notice. Licensed fonts are the client's responsibility.

## Sign-off

| FOR ACME CO. Signature, name, date | FOR DAN SOZANSKI Signature, name, date |
| --- | --- |